## lstQtr 2017
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE FIRST QUARTER, CY 2017
Province, City or Municipality: Taytay,Rizal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Philhealth Insurance | Mun of Taytay | 402219 | Jan 2015 | None | 31% | 123945 |  | continous program
Corporation-Chief of Facility
Philhealth Insurance | Mun of Taytay | 678486 | Jan 2015 | None | 18% | 122961.06 |  | continous program
Corporation-Hospital Charges
DSWD-Supplemental | Mun of Taytay | 4939200 | Aug 2,2016 | None | 80% | 3957888 |  | on going
Feeding Prog V | [7 empty] | implementation
Philhealth Insurance | Mun of Taytay | 2637763.5 | Aug 12,2015 | None | 44% | 1165306.22 |  | continous program
Corporation-Capitation
BFAR- Fishery Project | Mun of Taytay | 1000000 | Sept 30,2015 | None | 80% | 797038 |  | on going
implementation
DILG-DRRM training | Mun of Taytay | 500000 | Oct 2015 | None | 80% | 400100 |  | on going
implementation
DA- project such as | Mun of Taytay | 1700000 | July 21,2016 | None | 54% | 923125.5 |  | on going
trading post,swine fatteners | [7 empty] | implementation
Vermi-composting at LGU
DTI- livelihood projects | Mun of Taytay | 1550000 | Aug 12,2016 | None | 64% | 989800 |  | on going
implementation
DOLE - livelihood | Mun of Taytay | 3001400 | Oct 11,2016 | None | 83% | 2494600 |  | on going
implementation
DSWD-Bahay Pag Asa | Mun of Taytay | 2500000 | Nov 8,2016 | None | not yet |  |  | not yet
[5 empty] | implemented |  |  | implemented
DOH | Mun of Taytay | 550000 | Dec 28,2016 | None | on the process of |  |  | on the process of
[5 empty] | implementation |  |  | implementation
DILG | Mun of Taytay | 5900000 | Jan 22,2016 | None | on the process of |  |  | on the process of
[5 empty] | implementation |  |  | implementation
We hereby certify that we have reviewed the contents and hereby attest to the
veracity and correctness of the data or information contained in this document.
VIOLETA C. DEL MUNDO | [5 empty] | Hon . GEORGE RICARDO R. GACULA ll
Municipal Accountant | [5 empty] | Municipal Mayor

## BUB-CY2016
BUB FUND STATUS
CY 2016
Date of Fund Transfer | Source Agency | Amount Received | Disbursement for CY 2016 | Balance as of Dec 31,2016 | Purpose | Remarks
Aug 10,2015 | DILG | 600000 | 600000 | 0 | DRRM training | Project completed
Sept 30,2015 | BFAR | 1000000 |  | 1000000 | Fishery Project | on going implementation
Oct 2015 | DILG | 500000 |  | 500000 | DRRM training | on going implementation
Oct 2015 | DOLE | 5283550 | 5283550 | 0 | livelihood | Project completed
Jan 2016 | DSWD | 1500000 | 1500000 | 0 | Const. of OSCA facilities | Project completed
Jan 22,2016 | DILG | 5900000 |  | 5900000 | Rescue equipt,health wellness prog, | on going implementation
provision of furniture(arm chair)Renovation
of volunteer office
July 21,2016 | DA | 1700000 |  | 1700000 | project such as trading post, | on going implementation
swine fatteners, vermi-composting at LGU
Aug 12,2016 | DTI | 1550000 |  | 1550000 | livelihood project for T-shirt printing | on going implementation
Oct 11,2016 | DOLE | 3001400 | 999400 | 2002000 | livelihood projects -woodworks, | on going implementation
sewing machine,toda spareparts
Nov 8,2016 | DSWD | 2500000 |  | 2500000 | Bahay Pag Asa
Dec 28,2016 | DOH | 550000 |  | 550000 | Emergency Medical kit - Barangay | on going implementation
Health Station Kit
Prepared by:
Certified Correct:
RAQUEL T. BALTAZAR
Admin Asst l |  |  |  |  | VIOLETA C. DEL MUNDO
Municipal Accountant

## 4thQtr 2016
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE FOURTH QUARTER, CY 2016
Province, City or Municipality: Taytay,Rizal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Philhealth Insurance | Mun of Taytay | 392829 | Jan 2015 | None | 36.5% | 123945 |  | continous program
Corporation-Chief of Facility
Philhealth Insurance | Mun of Taytay | 656576 | Jan 2015 | None | 15% | 97928.31 |  | continous program
Corporation-Hospital Charges
DSWD-Supplemental | Mun of Taytay | 4939200 | Aug 2,2016 | None | 35% | 1705728 |  | on going
Feeding Prog V | [7 empty] | implementation
Philhealth Insurance | Mun of Taytay | 2637763.5 | Aug 12,2015 | None | 44% | 1165306.22 |  | continous program
Corporation-Capitation
BFAR- Fishery Project | Mun of Taytay | 1000000 | Sept 30,2015 | None | on going |  |  | on going
[5 empty] | implementation |  |  | implementation
DILG-DRRM training | Mun of Taytay | 500000 | Oct 2015 | None | project | 500000 |  | project implemented
implemented
DA- project such as | Mun of Taytay | 1700000 | July 21,2016 | None | on going |  |  | on going
trading post,swine fatteners |  |  |  |  | implementation |  |  | implementation
Vermi-composting at LGU
DTI- livelihood projects | Mun of Taytay | 1550000 | Aug 12,2016 | None | on going |  |  | on going
[5 empty] | implementation |  |  | implementation
DOLE - livelihood | Mun of Taytay | 3001400 | Oct 11,2016 | None | 33% | 999400 |  | on going
implementation
DSWD-Bahay Pag Asa | Mun of Taytay | 2500000 | Nov 8,2016 | None | not yet |  |  | not yet
[5 empty] | implemented |  |  | implemented
DOH | Mun of Taytay | 550000 | Dec 28,2016 | None | on the process of |  |  | on the process of
[5 empty] | implementation |  |  | implementation
DILG | Mun of Taytay | 5900000 | Jan 22,2016 | None | on the process of |  |  | on the process of
[5 empty] | implementation |  |  | implementation
We hereby certify that we have reviewed the contents and hereby attest to the
veracity and correctness of the data or information contained in this document.
VIOLETA C. DEL MUNDO | [5 empty] | Hon . GEORGE RICARDO R. GACULA ll
Municipal Accountant | [5 empty] | Municipal Mayor

## 3RDQtr 2016BUB
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
CY 2016
Province, City or Municipality: Taytay,Rizal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
BFAR- Fishery Project | Mun of Taytay | 1000000 | Sept 30,2015 | None | in process |  |  | in process
DILG-DRRM training | Mun of Taytay | 500000 | Oct 2015 | None | in process |  |  | in process
DA- project such as | Mun of Taytay | 1700000 | July 21,2016 | None | not yet |  |  | on going implementation
trading post,swine fatteners |  |  |  |  | implemented
Vermi-composting at LGU
DTI- livelihood projects | Mun of Taytay | 1550000 | Aug 12,2016 | None | not yet |  |  | on going implementation
implemented
DOLE IV-A | Mun of Taytay | 3001400 | Oct 11,2016 | None | on going |  |  | on going implementation
livelihood grants |  |  |  |  | implementation
DILG | Mun of Taytay | 5900000 | Jan 22,2016 |  | on the process of |  |  | on the process of
[5 empty] | implementation |  |  | implementation
DOH | Mun of Taytay | 550000 | Dec 2016
DSWD-Bahay Pag Asa | Mun of Taytay | 2500000 | Nov 2016
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
VIOLETA C. DEL MUNDO | [5 empty] | Hon . GEORGE RICARDO R. GACULA ll
Municipal Accountant | [5 empty] | Municipal Mayor

## 3RDQtr 2016
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE THIRD QUARTER, CY 2016
Province, City or Municipality: Taytay,Rizal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Philhealth Insurance | Mun of Taytay | 334164 | Jan 2015 | None | 36.5% | 121378 |  | continous program
Corporation-Chief of
Facility
Philhealth Insurance | Mun of Taytay | 517124 | Jan 2015 | None | 11% | 58940.65 |  | continous program
Corporation-Hospital
Charges
DSWD-Supplemental | Mun of Taytay | 4939200 | Aug 2,2016 | None | not yet |  |  | not yet implemented
Feeding Prog V |  |  |  |  | implemented
Philhealth Insurance | Mun of Taytay | 2637763.5 | Aug 12,2015 | None | 19% | 500339.58 |  | continous program
Corporation-Capitation
BFAR- Fishery Project | Mun of Taytay | 1000000 | Sept 30,2015 | None | not yet |  |  | not yet implemented
implemented
DILG-DRRM training | Mun of Taytay | 500000 | Oct 2015 | None | not yet |  |  | not yet implemented
implemented
DA- project such as | Mun of Taytay | 1700000 | July 21,2016 | None | not yet |  |  | not yet implemented
trading post,swine fatteners |  |  |  |  | implemented
Vermi-composting at LGU
DTI- livelihood projects | Mun of Taytay | 1550000 | Aug 12,2016 | None | not yet |  |  | not yet implemented
implemented
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
VIOLETA C. DEL MUNDO | [5 empty] | Hon . GEORGE RICARDO R. GACULA ll
Municipal Accountant | [5 empty] | Municipal Mayor

## 2ndQtr 2016
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE SECOND QUARTER, CY 2016
Province, City or Municipality: Taytay,Rizal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Philhealth Insurance | Mun of Taytay | 276317 | Jan 2015 | None | not yet | NA |  | continous program
Corporation-Chief of |  |  |  |  | implemented
Facility
Philhealth Insurance | Mun of Taytay | 485519 | Jan 2015 | None | 7% | 36446.8 |  | continous program
Corporation-Hospital
Charges
DSWD-Supplemental | Mun of Taytay | 4056000 | July 14,2015 | None | 100% | 4056000 |  | project completed
Feeding Prog V
Philhealth Insurance | Mun of Taytay | 2637763.5 | Aug 12,2015 | None | 19% | 500339.58 |  | continous program
Corporation-Capitation
DILG-DRRM training | Mun of Taytay | 600000 | Aug 10,2015 | None | 100% | 600000 |  | project completed
BFAR- Fishery Project | Mun of Taytay | 1000000 | Sept 30,2015 | None |  |  |  | not yet implemented
DILG-DRRM training | Mun of Taytay | 500000 | Oct 2015 | None |  |  |  | not yet implemented
DOLE - livelihood | Mun of Taytay | 5283550 | Oct 2015 | None | 100% | 5283550 |  | project completed
DSWD- OSCA facilities | Mun of Taytay | 1500000 | Jan 2016 | None | 100% | 1498361.27 |  | project completed
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
VIOLETA C. DEL MUNDO | [5 empty] | Hon . GEORGE RICARDO R. GACULA ll
Municipal Accountant | [5 empty] | Municipal Mayor

## lstQtr 2016
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE FIRST QUARTER, CY 2016
Province, City or Municipality: Taytay,Rizal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Philhealth Insurance | Mun of Taytay | 235367 | Jan 2015 | None | not yet | NA |  | continous program
Corporation-Chief of |  |  |  |  | implemented
Facility
Philhealth Insurance | Mun of Taytay | 389969 | Jan 2015 | None | 9% | 34288.8 |  | continous program
Corporation-Hospital
Charges
DSWD-Supplemental | Mun of Taytay | 4056000 | July 14,2015 | None | 92% | 3744000 |  | in process
Feeding Prog V
Philhealth Insurance | Mun of Taytay | 2637763.5 | Aug 12,2015 | None | 19% | 500339.58 |  | continous program
Corporation-Capitation
DILG-DRRM training | Mun of Taytay | 600000 | Aug 10,2015 | None | 99% | 599680 |  | in process
BFAR- Fishery Project | Mun of Taytay | 1000000 | Sept 30,2015 | None |  |  |  | not yet implemented
DILG-DRRM training | Mun of Taytay | 500000 | Oct 2015 | None |  |  |  | not yet implemented
DOLE - livelihood | Mun of Taytay | 5283550 | Oct 2015 | None | 41% | 2140819 |  | in process
DSWD- OSCA facilities | Mun of Taytay | 1500000 | Jan 2016 | None |  |  |  | not yet implemented
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
LUZETH G. MA | [5 empty] | Hon . JANET DL. MERCADO
Municipal Accountant-OIC | [5 empty] | Municipal Mayor

## 4thQtr 2015
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE FOURTH QUARTER, CY 2015
Province, City or Municipality: Taytay,Rizal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Philhealth Insurance | Mun of Taytay | 114847 | Jan 2015 | None | not yet | NA |  | continous program
Corporation-Chief of |  |  |  |  | implemented
Facility
Philhealth Insurance | Mun of Taytay | 119589 | Jan 2015 | None | 26% | 23991.55 |  | continous program
Corporation-Hospital
Charges
DOLE- livelihood | Mun of Taytay | 762690 | Feb 18,2015 | None | 100% | 762690 |  | project completed
DSWD-Supplemental | Mun of Taytay | 4056000 | July 14,2015 | None | 69% | 2808000 |  | in process
Feeding Prog V
Philhealth Insurance | Mun of Taytay | 2637763.5 | Aug 12,2015 | None | 19% | 500339.58 |  | continous program
Corporation-Capitation
DILG-DRRM training | Mun of Taytay | 600000 | Aug 10,2015 | None | 63% | 376150 |  | not yet implemented
BFAR- Fishery Project | Mun of Taytay | 1000000 | Sept 30,2015 | None |  |  |  | not yet implemented
DILG-DRRM training | Mun of Taytay | 500000 | Oct 2015 | None |  |  |  | not yet implemented
DOLE - livelihood | Mun of Taytay | 5283550 | Oct 2015 | None |  |  |  | not yet implemented
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
LUZETH G. MA | [5 empty] | Hon . JANET DL. MERCADO
Municipal Accountant-OIC | [5 empty] | Municipal Mayor

## 3rdQtr 2015
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE THIRD QUARTER, CY 2015
Province, City or Municipality: Taytay,Rizal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Philhealth Insurance | Mun of Taytay | 101892 | Jan 2015 | None | not yet | NA |  | continous program
Corporation-Chief of |  |  |  |  | implemented
Facility
Philhealth Insurance | Mun of Taytay | 91434 | Jan 2015 | None | 26% | 23991.55 |  | continous program
Corporation-Hospital
Charges
DOLE- livelihood | Mun of Taytay | 762690 | Feb 18,2015 | None | 100% | 762690 |  | project completed
DSWD-Supplemental | Mun of Taytay | 4056000 | July 14,2015 | None | 17% | 702000 |  | in process
Feeding Prog V
Philhealth Insurance | Mun of Taytay | 1009450 | Aug 12,2015 | None | 20% | 100945 |  | continous program
Corporation-Capitation
DILG-DRRM training | Mun of Taytay | 600000 | Aug 10,2015 | None |  |  |  | not yet implemented
BFAR- Fishery Project | Mun of Taytay | 1000000 | Sept 30,2015 | None |  |  |  | not yet implemented
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
LUZETH G. MA | [5 empty] | Hon . JANET DL. MERCADO
Municipal Accountant-OIC | [5 empty] | Municipal Mayor

## 2ndQtr 2015
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2ND QUARTER, CY 2015
Province, City or Municipality: Taytay,Rizal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Philhealth Insurance | Mun of Taytay | 101892 | Jan 2015 | None | not yet | NA |  | continous program
Corporation-Chief of |  |  |  |  | implemented
Facility
Philhealth Insurance | Mun of Taytay | 91434 | Jan 2015 | None | 26% | 23991.55 |  | continous program
Corporation-Hospital
Charges
DOLE | Mun of Taytay | 762690 | Feb 18,2015 |  | 80% | 613327 |  | in process
DSWD - Region lV | Mun of Taytay | 1729200 | Jan 14,2015 |  | 100% | 1729200 |  | project completed
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
LUZETH G. MA | [5 empty] | JANET DL. MERCADO
Municipal Accountant-OIC | [5 empty] | Municipal Mayor

## lstQtr 2015
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE FIRST QUARTER, CY 2015
Province, City or Municipality: Taytay,Rizal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Philhealth Insurance | Mun of Taytay | 6590 | Jan 2015 | None | not yet | NA |  | continous program
Corporation-Chief of |  |  |  |  | implemented
Facility
Philhealth Insurance | Mun of Taytay | 13210 | Jan 2015 | None | 26% | 8225 |  | continous program
Corporation-Hospital
Charges
DOLE | Mun of Taytay | 762690 | Feb 18,2015 |  | 90% | 625207 |  | in process
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
LUZETH G. MA | [5 empty] | JANET DL. MERCADO
Municipal Accountant-OIC | [5 empty] | Municipal Mayor

## 4thQtr-2014
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4TH QUARTER, CY 2014
Province, City or Municipality: Taytay,Rizal
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
PCSO | Mun of Taytay | 2322943.39 | Dec 15,2014 | None | 12% | 270200 |  | continous program
Philhealth Insurance | Mun of Taytay | 62706 |  | None | not yet | NA |  | continous program
Corporation |  |  |  |  | implemented
Philhealth Insurance | Mun of Taytay | 146314 | Dec 23,2014 | None | 18% | 26180 |  | continous program
Corporation
Philhealth Insurance | Mun of Taytay | 599750 |  | None | not yet |  |  | continous program
Corporation |  |  |  |  | implemented
DOLE | Mun of Taytay | 762690 | 1st Qtr of 2015 |  | not yet |  |  | to be implemented on 2015
implemented
DSWD - Region lV | Mun of Taytay | 1729200 | 1st Qtr of 2015 |  | not yet |  |  | to be implemented on 2015
implemented
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
LUZETH G. MA | [5 empty] | JANET DL. MERCADO
Municipal Accountant-OIC | [5 empty] | Municipal Mayor

## DILG-Mayors
BUB
FY 2014
Agency | Amount Received | Amount Utilized | Date Received
DOLE | 762690 | 762690 | Oct 24,2014 | 100%
| 762690 | 762690
FY 2015
DILG-DRRM training | 600000 | 600000 | Aug 10,2015 | 100%
BFAR- Fishery Project | 1000000 | 800000 | Sept 30,2015 | 80% completed
DILG-DRRM training | 500000 | 500000 | Oct 2015 | 100%
DOLE - livelihood | 5283550 | 5283550 | Oct 2015 | 100%
| 7383550 | 7183550
FY 2016
DSWD- OSCA facilities | 1500000 | 1500000 | Jan 2016
DILG | 5900000 |  | Jan 22,2016
DA- project such as | 1700000 | 1700000 | July 21,2016 | 64% completed
trading post,swine fatteners
Vermi-composting at LGU
DTI- livelihood projects | 1550000 | 989800 | Aug 12,2016 | 64% completed
DOLE - livelihood | 3001400 | 3001400 | Oct 11,2016
DSWD-Bahay Pag Asa | 2500000 |  | Nov 2016
DOH | 550000 |  | Dec 2016
16701400
Vermi-composting at LGU
[5 empty] | DA- project such as | Mun of Taytay | 1700000 | July 21,2016
DTI- livelihood projects | 1550000 |  | Aug 12,2016 |  | trading post,swine fatteners
Vermi-composting at LGU
DOLE IV-A | 3001400 |  | Oct 11,2016
livelihood grants |  |  |  |  | DTI- livelihood projects | Mun of Taytay | 1550000 | Aug 12,2016
DILG | 5900000 |  | Jan 22,2016
DOH | 550000 |  | Dec 2016
DSWD-Bahay Pag Asa | 2500000 |  | Nov 2016